# Software Effort Estimation

Project: MediLab, a Multi Tenant Diagnostic Lab Marketplace and Appointment Platform Technique: Use Case Points (UCP) Author: Victoria Dowana (Student ID: 22425077) Date: 2026-08-12

This document builds directly on the functional requirements and actors defined in SRS.md. Its conclusions are folded into Section 7 (“Software Effort Estimation”) of the consolidated Project Documentation.

## Functional Requirement Reference

FR IDs referenced throughout the Use Case Points calculation below map to the following requirements, defined in full (with priority) in SRS.md §5:

| ID | What it covers |
| --- | --- |
| FR1 | Patient can register an account |
| FR2 | User can log in / log out (all roles) |
| FR3 | Patient can search the standardized test catalog by name/category |
| FR4 | Patient can view all labs offering a matched test, with price, location, and turnaround time (comparison view) |
| FR5 | Patient can filter/sort comparison results by price, location, or turnaround time |
| FR6 | Patient can view a lab’s profile (name, address, contact, offered tests) |
| FR7 | Patient can book an appointment with a specific lab, for a specific test offering and slot |
| FR8 | System displays prep instructions before booking confirmation |
| FR9 | Patient can view their own appointments and status across all labs they’ve booked with |
| FR10 | Patient can cancel an upcoming appointment |
| FR11 | Patient can reschedule an upcoming appointment |
| FR12 | Lab staff can log in, scoped to their own lab |
| FR13 | Lab staff can view their lab’s queue of today’s/upcoming appointments |
| FR14 | Lab staff can mark a sample as collected (records status and timestamp) |
| FR15 | Lab staff can advance an appointment/sample’s status along the defined pipeline |
| FR16 | Lab staff can view a single patient’s appointment detail (within their own lab only) |
| FR17 | Lab admin can register their lab on the platform (submits a profile for platform admin approval) |
| FR18 | Lab admin can manage their lab’s profile (name, address, contact info) |
| FR19 | Lab admin can manage staff accounts for their lab |
| FR20 | Lab admin can add/edit/deactivate their lab’s test offerings (select from the platform test catalog; set price, turnaround time, prep instructions) |
| FR21 | Lab admin can view basic operational statistics for their own lab |
| FR22 | Platform admin can review and approve or reject new lab registrations |
| FR23 | Removed in v2.1 (was: platform admin manages the global standardized test catalog). See SRS.md §5 change note; the ID is retained but unused. |
| FR24 | Platform admin can suspend or reinstate a lab |
| FR25 | Platform admin can view platform wide operational statistics (labs, bookings, tests) |
| FR26 | System prevents two appointments from being booked into the same lab’s same slot |
| FR27 | System enforces strict multi tenant data isolation: lab staff/admin can only ever access their own lab’s data |
| FR28 | Added in v2.2, post delivery (not part of the original UCP estimated scope below): lab admin can add a new test to the shared platform catalog when the one they need doesn’t already exist |

## 1. Technique Selection & Justification

Selected: Use Case Points (UCP)

Alternatives considered and rejected for this specific project:

- COCOMO/COCOMO II: requires an upfront size estimate (KLOC or a calibrated proxy) that isn’t knowable before any code exists; better suited to later re estimation once a codebase exists to size.

- Story Points: requires a historical team velocity to convert points into time; there is no prior sprint history for this team, so points would have to be arbitrarily anchored anyway.

- Expert estimation (pure): reasonable as a sanity check, but too coarse a basis on its own to defend the estimate to a client or stakeholder, especially given the added architectural risk of multi tenancy.

UCP was chosen because the requirements in SRS.md are already actor- and use case shaped (Patient, Lab Staff, Lab Admin, Platform Admin; a clear list of discrete use cases per role), so actors and use cases can be classified directly from the SRS without extra translation, and the method produces a traceable effort number broken into inputs that can be independently re checked.

## 2. Use Case Points Calculation

### 2.1 Actor Weighting (UAW)

All four actors are humans interacting through a GUI → classified Complex (weight 3).

| Actor | Type | Weight |
| --- | --- | --- |
| Patient | Complex (GUI) | 3 |
| Lab Staff | Complex (GUI) | 3 |
| Lab Admin | Complex (GUI) | 3 |
| Platform Admin | Complex (GUI) | 3 |
| UAW (total) |  | 12 |

### 2.2 Use Case Weighting (UUCW)

Classified by transaction count: Simple (≤3) = 5, Average (4–7) = 10, Complex (>7) = 15. Every use case at Must have or Should have priority in SRS.md §7 is counted; Could have and Won’t have are excluded.

| Use Case | FRs | Priority | Transactions (approx.) | Class | Weight |
| --- | --- | --- | --- | --- | --- |
| Register (Patient) | FR1 | Must | 3 | Simple | 5 |
| Login/Logout (shared, all roles) | FR2 | Must | 2 | Simple | 5 |
| Search & Compare Labs for a Test | FR3, FR4 | Must | 5: search term → query test catalog → query cross tenant offerings → aggregate results → render comparison | Average | 10 |
| Filter/Sort Comparison Results | FR5 | Should | 3 | Simple | 5 |
| View Lab Profile | FR6 | Should | 2 | Simple | 5 |
| Book Appointment | FR7, FR8, FR26 | Must | 8: select lab offering → check slot availability (scoped to lab) → validate → display prep instructions → confirm → reject on clash → persist → confirm to user | Complex | 15 |
| View My Appointments/Status | FR9 | Must | 2 | Simple | 5 |
| Cancel Appointment | FR10 | Should | 3 | Simple | 5 |
| View Today’s Queue (Lab Staff) | FR13 | Must | 3 | Simple | 5 |
| Update Appointment/Sample Status | FR14, FR15 | Must | 5: select appt → validate transition → update → timestamp → persist | Average | 10 |
| View Patient Appointment Detail | FR16 | Should | 2 | Simple | 5 |
| Lab Registration / Onboarding | FR17 | Must | 5: fill lab profile → submit → validate → create pending record → confirmation | Average | 10 |
| Manage Lab Profile | FR18 | Must | 3 | Simple | 5 |
| Manage Staff Accounts | FR19 | Should | 4: add/edit/remove/list | Average | 10 |
| Manage Test Offerings (CRUD) | FR20 | Must | 6 | Average | 10 |
| View Lab Stats | FR21 | Should | 2 | Simple | 5 |
| Review & Approve Lab Registration | FR22 | Must | 5: view pending → review → approve/reject → notify → persist | Average | 10 |
| Suspend/Reinstate Lab | FR24 | Should | 3 | Simple | 5 |
| View Platform wide Stats | FR25 | Should | 2 | Simple | 5 |
| UUCW (total) |  |  |  |  | 135 |

(v2.1: “Manage Global Test Catalog” / FR23 removed, see SRS.md §5 change note. Platform admin’s scope is lab lifecycle only; Test is fixed seeded data for the initial release, not an admin use case.)

UUCP (Unadjusted Use Case Points) = UAW + UUCW = 12 + 135 = 147

### 2.3 Technical Complexity Factor (TCF)

TCF = 0.6 + (0.01 × ΣTFactor), factors rated 0 (irrelevant) – 5 (essential).

| Factor | Weight | Rating | Weighted |
| --- | --- | --- | --- |
| T1 Distributed system | 2 | 2 | 4 |
| T2 Performance objectives | 1 | 3 | 3 |
| T3 End user efficiency | 1 | 4 | 4 |
| T4 Complex internal processing | 1 | 4 | 4 |
| T5 Reusability | 1 | 2 | 2 |
| T6 Easy to install | 0.5 | 4 | 2 |
| T7 Easy to use | 0.5 | 4 | 2 |
| T8 Portability | 2 | 3 | 6 |
| T9 Easy to change | 1 | 3 | 3 |
| T10 Concurrency | 1 | 3 | 3 |
| T11 Security objectives | 1 | 5 | 5 |
| T12 Third party access | 1 | 0 | 0 |
| T13 Special training needed | 1 | 2 | 2 |
| ΣTFactor |  |  | 40 |

TCF = 0.6 + (0.01 × 40) = 1.00

Ratings that changed materially from a single tenant design, briefly justified: - T4 Complex internal processing (rated 4, up from a single lab baseline of 2): cross tenant search/comparison queries, tenant scoped filtering on every request, and an approval workflow are genuinely more complex than single lab CRUD. - T11 Security objectives (rated 5, up from 4): multi tenant data isolation (NFR2, NFR7) is a hard requirement, since a leak here exposes one lab’s patient data to another lab, not just a routine access control bug. - T1 Distributed system (rated 2, up from 1): still a single deployed application and database, not physically distributed, but logical multi tenancy introduces distribution like reasoning (per tenant scoping on every query), so it is no longer rated at the floor. - T10 Concurrency (rated 3, up from 2): many labs’ staff and many patients transacting concurrently against shared slot booking logic is a more realistic concern than a single lab’s queue. - T13 Special training needed (rated 2, up from 1): four distinct roles (vs. three) with a lab onboarding/approval flow require slightly more onboarding material than a single lab app.

### 2.4 Environmental Factor (EF)

EF = 1.4 + (-0.03 × ΣEFactor), factors rated 0–5.

| Factor | Weight | Rating | Weighted |
| --- | --- | --- | --- |
| E1 Familiarity with dev process | 1.5 | 3 | 4.5 |
| E2 Application experience | 0.5 | 3 | 1.5 |
| E3 OO/web framework experience | 1 | 4 | 4 |
| E4 Lead analyst capability | 0.5 | 3 | 1.5 |
| E5 Motivation | 1 | 5 | 5 |
| E6 Stable requirements | 2 | 2 | 4 |
| E7 Part time staff (negative factor) | -1 | 0 | 0 |
| E8 Difficult programming language (negative factor) | -1 | 1 | -1 |
| ΣEFactor |  |  | 19.5 |

EF = 1.4 + (-0.03 × 19.5) = 0.815

Ratings that changed materially, briefly justified: - E6 Stable requirements (rated 2, down from 3): a multi tenant marketplace has more moving parts whose shape can shift once real labs start onboarding (e.g. how pricing tiers or approval rules should work), so requirements are less firmly settled than a single tenant app’s would be at this stage.

### 2.5 Adjusted Use Case Points

UCP = UUCP × TCF × EF = 147 × 1.00 × 0.815 ≈ 120 UCP

## 3. From UCP to Effort, Person Hours, and Duration

The textbook default of ~20 person hours/UCP is calibrated for a larger multi person team building production grade enterprise software, including significant coordination overhead. That default is closer to appropriate here than it would be for a single tenant app, given the added architectural risk of multi tenancy, but a small, tool assisted team can still reasonably operate below it. A three point (PERT style) range is used instead of a single asserted multiplier, so the uncertainty stays visible:

| Scenario | hrs/UCP | Basis | Effort (120 UCP) |
| --- | --- | --- | --- |
| Optimistic | 2.5 | Heavy reuse of scaffolding, hosted auth, ORM tooling, and a well tested tenant isolation pattern from day one; no unexpected blockers | 300h |
| Most likely | 3.5 | Normal implementation pace including typical debugging, code review, and stakeholder feedback cycles | 420h |
| Pessimistic | 5.5 | Tenant isolation bugs discovered late, lab onboarding workflow requiring rework after stakeholder feedback, integration friction | 660h |

PERT expected effort = (Optimistic + 4×Most likely + Pessimistic) / 6 = (300 + 4×420 + 660) / 6 ≈ 440 person hours

### Full lifecycle rollup

The UCP derived figure covers design, implementation, and testing of the use case shaped functionality. Requirements/planning and deployment/documentation scale with process overhead and the number of distinct role based surfaces (patient app, lab console, platform admin console) rather than with use case count, so they are estimated separately:

| Phase | Estimated effort |
| --- | --- |
| Requirements & planning | ~16h |
| Design + Implementation + Testing (UCP derived, PERT expected) | ~440h |
| Deployment | ~12h |
| Documentation | ~18h |
| Total (full lifecycle) | ~486 person hours |

### Duration

| Team composition | Estimated duration |
| --- | --- |
| One developer, full time (~40h/week) | ~12 weeks (~3 months) |
| One developer, part time/consulting pace (~20h/week) | ~24 weeks (~6 months) |
| Two developer team (patient facing + lab/platform admin split) | ~6–7 weeks |
| Three developer team (patient app / lab console / platform admin + shared backend) | ~4–5 weeks |

Recommended checkpoint: at roughly 40% of the estimated core build effort, review whether the Must have surface is on track, specifically whether tenant data isolation (FR27, NFR2) is proven correct under test by that point, since it is the requirement whose failure mode is most severe (a cross tenant data leak). If isolation testing is not passing cleanly at that checkpoint, treat it as the top priority over any remaining Should have feature work.

## 4. Assumptions

- The developer(s) have working proficiency in the chosen web stack going in, including familiarity with implementing row level or schema level multi tenancy, rather than learning it from zero during the build.

- Requirements are locked prior to implementation start for the Must have set; the marketplace specific Should have items (staff management, platform stats) may still see minor refinement without triggering a full re estimate.

- Tooling (framework scaffolding, ORM/migrations, managed auth libraries, and an established tenant scoping pattern) is used rather than building primitives from scratch.

- Cost effective hosting is acceptable for the initial deployment; no bespoke infrastructure provisioning beyond that.

- The initial release onboards a small number of pilot labs, not an open self serve marketplace at scale.

## 5. Constraints

- Delivery is scoped to a defined initial release; effort beyond that is a separate future estimate (see SRS.md §9).

- A small, dedicated team delivers the initial release; see the team composition options in §3.

- Hosting is cost effective/pilot tier initially, which bounds achievable performance/availability guarantees (see NFR9 in SRS.md).

- No budget is allocated for a formal, independent security audit in the initial release; tenant isolation testing is the highest priority item within the testing budget that is allocated (see Testing_Report.md).

## 6. How This Estimate Shaped Scope

- Book Appointment remains the single Complex use case (15 pts), but is now materially riskier than in a single tenant design because slot availability checks and clash prevention must be correctly scoped per lab, which kept it Must have with an explicit note that it needs the most testing attention.

- Search & Compare Labs for a Test, Lab Registration/Onboarding, and Review & Approve Lab Registration are the three use cases that exist because this is a marketplace rather than a single tenant app; all three are Must have, since without them there is no multi tenant value proposition at all: a lab can’t join, an admin can’t vet it, and a patient can’t discover it.

- Ratings/reviews, real geo distance search, and richer platform analytics were the clearest candidates for Won’t have: they add UUCW without being necessary for the core “find a lab, compare, book” loop.

- The jump from a single tenant UCP of ~59 to a multi tenant UCP of ~120, roughly 2.0 times, not a modest increment, is the direct, traceable consequence of adding a fourth actor and the onboarding/comparison use cases; this is presented explicitly so the effort implication of the multi tenant pivot is visible rather than absorbed silently into a schedule.

- The tenant isolation checkpoint in §3 exists because, unlike a feature gap, an isolation failure is a trust destroying defect for a marketplace. It is treated as the one item that overrides Should have work if the two compete for time.

## 7. Final Locked In Scope for the Initial Release

Committed (Must have): patient registration/login, cross tenant test search and comparison (price/location/turnaround), appointment booking with prep instruction display and per lab slot clash prevention, patient status view, lab staff login and queue/status management scoped to their lab, lab registration and profile management, lab test offering CRUD, platform admin lab approval, strict multi tenant data isolation enforced server side.

Stretch (Should have, built only if Must have lands ahead of schedule): result filtering/sorting, lab profile pages, appointment cancellation, staff single patient detail view, lab staff account management, lab level and platform level stats, lab suspend/reinstate, auditable platform admin actions.

Deferred (Could/Won’t have): reschedule flow, lab ratings/reviews, real geo distance search, real payment processing, real result values/files, native mobile app, insurance/LIS integrations, advanced analytics dashboards, automated listing review, multi currency/localisation; all carried forward into the Technical Debt Plan and Future Evolution section.

This scope is the one design and implementation proceed against; any change to it must be re checked against this estimate before implementation continues.